## Sheet1
Date | Facility | Shutdown Task | Department | Planned Days | Actual Days | Budget Spent | Safety Incidents
2026-05-01 | Plant Alpha | Core Boiler Deep Inspection | Mechanical | 5 | 5 | 150000 | 0
2026-05-06 | Plant Alpha | Main Piping Infrastructure | Piping | 10 | 12 | 340000 | 1
2026-05-18 | Plant Alpha | High-Pressure Turbine Overhaul | Electrical | 14 | 13 | 500000 | 0
2026-05-01 | Plant Alpha | Chemical Catalyst Changeout | Process | 7 | 8 | 220000 | 0
2026-05-01 | Plant Beta | Safety Valve Recertification | Mechanical | 4 | 4 | 90000 | 0
2026-05-05 | Plant Beta | High-Volume Vessel Cleaning | Process | 6 | 7 | 110000 | 1
2026-05-12 | Plant Beta | Main Substation Maintenance | Electrical | 5 | 5 | 130000 | 0
2026-05-17 | Plant Beta | Primary Flare Header Repair | Piping | 12 | 15 | 410000 | 0